## Hourlist
Hourlist
Name | Piia
Day | Task | Details | Planned Hours | Hours of Work | Diff.
2020-06-01 | Installing Unity, Experimentation, Tutorials | After installing Unity I read up on some of the manuals that were sent to me and experimented with Unity, I created some GameObjects and Scenes. I created the hourlist. I watched the tutorial series "How to make a Video Game in Unity". | 6 | 6 | 0
2020-06-02 | Fixing Unity Editor, more Experimentation, Tutorials and Movement | The Unity editor suddenly didn't work and told me that something is wrong with my firewall. After trying to fix it for a while, I decided to install an older version of the editor and had no problems afterwards. I watched tutorials on movement, C# and experimented some with physics. | 6 | 6 | 0
2020-06-03 | Finishing tutorial series, watching and reading C# guides, creating small game concept | I finished the tutorial series "How to make a Video Game in Unity" and started using what I learned in Unity. I thought of a small game concept that I could have ready by the end of this week as well as started working on it. I also watched some C# and Unity guides. | 6 | 6 | 0
2020-06-04 | Working on creating the small game and a work-in-progress showcase for the talk. | Created two scripts, one for movement and one for camera. Created some GameObjects and materials. | 6 | 6 | 0
2020-06-05 | Working on finishing the demo and uploading it on GitHub | Experimenting with the camera and skybox color. Finishing the small demo, build the demo and upload it. | 6 | 6 | 0
2020-06-08 | Watching Tutorials and experimenting in Unity | Watching the Tutorial from Jason Weiman and checking out the Roguelike tutorial, as well as trying out some things in Unity that I learned. | 6 | 6 | 0
2020-06-09 | Tutorials, research and thinking of a small demo concept | I did some experimentation with Unity on how to make a 2D game, I left it very unpolished for now. I also learned a bit more about C# and then I started to work out a concept for a small 2D game demo that I could get done ideally till Friday. | 6 | 6 | 0
2020-06-10 | Following the weekly plan for learning C#, creating a small 2D game | I am trying to use all the C# function in the weekly plan and I'm trying to create a similar 2D game as in the Jason Weimann tutorial without looking up much, but still doing research if needed. | 6 | 6 | 0
2020-06-11 | Continuing to make the small game and doing research | Continuing what I did the day before. | 6 | 6 | 0
2020-06-12 | Planned out a schedule and a concept, watched Tutorials and did some testing | Planned schedule and watched Tutorials on how to make Zelda like games in Unity, I also used the work I did so far to think and experiment how I could build the game. | 6 | 6 | 0
2020-06-15 | Started research on how to build the game, started work on movement and wrote the schedule | Continued work from last time and wrote the schedule, as well as started working on the movement. | 6 | 6 | 0
2020-06-16 | Researched how the prototype should look and continued work on the base | Continued work from yesterday and researched sprites, which sprites to use or to create own ones, but decided to not make sprites from scratch. | 6 | 6 | 0
2020-06-17 | Continued work on the movement and started work on some objects | I started work on a box that can be pushed around and it should respond on how fast the player is. I also continued doing some research and worked on the movement. The player should be able to sprint, while pressing down a button. | 6 | 6 | 0
2020-06-18 | Improved the movement script and continued work on the objects | Essentially continued the work from yesterday and made some improvements. | 6 | 6 | 0
2020-06-19 | Watched a tutorial series on how to use sprites and charactersheets in unity | Watched the tutorials and then started work on some sprites, I later decided to first use free resources as placeholder. | 6 | 6 | 0
| - | -
|  |  | 90 | 90 | 0