## Hourlist
Hourlist
Name | Piia Laine
Categories
Day | Task | Details | Planning | Research | Coding | Total
2020-06-01 | Installing Unity, Experimentation, Tutorials | After installing Unity I read up on some of the manuals that were sent to me and experimented with Unity, I created some GameObjects and Scenes. I created the hourlist. I watched the tutorial series "How to make a Video Game in Unity". | 1 | 3 | 2 | 6
2020-06-02 | Fixing Unity Editor, more Experimentation, Tutorials and Movement | The Unity editor suddenly didn't work and told me that something is wrong with my firewall. After trying to fix it for a while, I decided to install an older version of the editor and had no problems afterwards. I watched tutorials on movement, C# and experimented some with physics. | 0 | 3 | 3 | 6
2020-06-03 | Finishing tutorial series, watching and reading C# guides, creating small game concept | I finished the tutorial series "How to make a Video Game in Unity" and started using what I learned in Unity. I thought of a small game concept that I could have ready by the end of this week as well as started working on it. I also watched some C# and Unity guides. | 0.5 | 3 | 2.5 | 6
2020-06-04 | Working on creating the small game and a work-in-progress showcase for the talk. | Created two scripts, one for movement and one for camera. Created some GameObjects and materials. | 0 | 2 | 4 | 6
2020-06-05 | Working on finishing the demo and uploading it on GitHub | Experimenting with the camera and skybox color. Finishing the small demo, build the demo and upload it. | 0 | 0.5 | 5.5 | 6
2020-06-08 | Watching Tutorials and experimenting in Unity | Watching the Tutorial from Jason Weiman and checking out the Roguelike tutorial, as well as trying out some things in Unity that I learned. | 0 | 4 | 2 | 6
2020-06-09 | Tutorials, research and thinking of a small demo concept | I did some experimentation with Unity on how to make a 2D game, I left it very unpolished for now. I also learned a bit more about C# and then I started to work out a concept for a small 2D game demo that I could get done ideally till Friday. | 2 | 1 | 3 | 6
2020-06-10 | Following the weekly plan for learning C#, creating a small 2D game | I am trying to use all the C# function in the weekly plan and I'm trying to create a similar 2D game as in the Jason Weimann tutorial without looking up much, but still doing research if needed. | 0 | 2 | 4 | 6
2020-06-11 | Continuing to make the small game and doing research | Continuing what I did the day before. | 0 | 2 | 4 | 6
2020-06-12 | Planned out a schedule and a concept, watched Tutorials and did some testing | Planned schedule and watched Tutorials on how to make Zelda like games in Unity, I also used the work I did so far to think and experiment how I could build the game. | 2.5 | 2 | 1.5 | 6
2020-06-15 | Started research on how to build the game, started work on movement and wrote the schedule | Continued work from last time and wrote the schedule, as well as started working on the movement. | 2 | 2 | 2 | 6
2020-06-16 | Researched how the prototype should look and continued work on the base | Continued work from yesterday and researched sprites, which sprites to use or to create own ones, but decided to not make sprites from scratch. | 1 | 3 | 2 | 6
2020-06-17 | Continued work on the movement and started work on some objects | I started work on a box that can be pushed around and it should respond on how fast the player is. I also continued doing some research and worked on the movement. The player should be able to sprint, while pressing down a button. | 0.5 | 1.5 | 4 | 6
2020-06-18 | Improved the movement script and continued work on the objects | Essentially continued the work from yesterday and made some improvements. | 0 | 2 | 4 | 6
2020-06-19 | Watched a tutorial series on how to use sprites and charactersheets in unity | Watched the tutorials and then started work on some sprites, I later decided to first use free resources as placeholder. | 0 | 1.5 | 4.5 | 6
2020-06-22 | Searching a free tileset, research as to how tilesets work in Unity and working in Unity | Read a tutorial about tilesets and continued working on my 2D Zelda-like game. | 0 | 4 | 2 | 6
2020-06-23 | Research on how to set up the camera and how to animate sprites, as well as how to make a pushable object | I watched a tutorial on how to make the camera similar to Zelda: A Link to the Past. Then I continued to research how to animate my player character. | 0 | 3.5 | 2.5 | 6
2020-06-24 | Continuing the work from yesterday | Continued work on the camera and animations. Managed to get the camera not go beyond the borders of the world. | 0 | 3 | 3 | 6
2020-06-25 | Watching Tutorials on Unity's blend tree and trying to implement it and tilesets | Animating my player character with Unity's blend tree feature. Used grids in Unity to make a tilemap with the tileset that I downloaded. | 0 | 3 | 3 | 6
2020-06-26 | Working on creating tilemaps in Unity, but had some troubles with it, so I tried the software Tiled | I watched a tutorial on the Tiled software and created tilemaps with it and continued the work on the animations. | 0 | 1.5 | 4.5 | 6
2020-06-29 | Importing the Tiled tilemaps to Unity and working on room transitions | Finished 3 tilemaps and imported them into Unity with the software Tiled2Unity. I had a few problems with the import, but then managed to get it working well. I started work on the room transitions. | 0 | 2 | 4 | 6
2020-06-30 | Finishing the first demo | Finished the room transitions and made a small text that shows the location when you enter a new room. Along with some refinement, I finished the demo. | 0 | 1 | 5 | 6
2020-07-01 | Research on how NPCs and dialogue work, trying to implement it, adding categories to the hourlist | Adding categories to the hourlist. I tried to implement NPCs and their dialogue. I planned ahead on how to continue with the project. | 1.5 | 1.5 | 3 | 6
2020-07-02 | Dialogue with NPC and signs, Project Management | Configuring, collisions, trigger zones and input settings in Unity, as well as doing project management work. | 3 | 1 | 2 | 6
2020-07-03 | Sound Effects and Audio in Unity, Project Management | Research on how to use sound effects and music in Unity. | 2 | 3 | 1 | 6
2020-07-06 | Designing some levels in Tiled and working animations | Working on the attack animation and started work on levels for the final version. | 0 | 1 | 5 | 6
2020-07-07 | Research State Machine and continue animations | Gaining knowledge on states in Unity and implement it, along with attack animations. | 0 | 3 | 3 | 6
2020-07-08 | Continuing work from the previous day | Continuing. | 0 | 1.5 | 4.5 | 6
2020-07-09 | Starting making a small website for access to the game | Starting a small showcase website with Svelte and PHP and continued the work from last time. | 0 | 0 | 6 | 6
2020-07-10 | Starting work on a pushable object | Research how to use collisions and kinematic bodies, as well as other body types to make a pot pushable. | 0 | 3.5 | 2.5 | 6
2020-07-13 | Continuing the work from last time and planning the UI for the website | Continuing with the movable pot and the website. | 0 | 3 | 3 | 6
2020-07-14 | Project Management and continuing the pushable objects | Started work on a showcase document that displays how the game works and its features. | 2 | 1 | 3 | 6
2020-07-15 | Starting to work on a switch, finishing the moving object | Finished the object and now working on a switch that triggers something to appear or disappear. | 0.5 | 1 | 4.5 | 6
2020-07-16 | Continuing work on the Switch and adding Sound Effects | Continuing the work from yesterday and adding a sound manager to use sound effects. | 0 | 1 | 5 | 6
2020-07-17 | Finishing the switch and creating a small demo as a showcase | Working on displaying all new features in a demo. | 0 | 1.5 | 4.5 | 6
2020-07-20 | Finishing the demo and doing Project Management | Finishing the demo and updating the hourlist, as well as the showcase document. | 1 | 0.5 | 4.5 | 6
0
| - | - |  |  |  | 0
|  |  | 19.5 | 73 | 123.5 | 216